## SGOD-CONSOLIDATION-1st-QTR
1st QUARTER PROGRAM IMPLEMENTATION REVIEW FOR CY 2026-CONSOLIDATED- REPORT- SGOD
SGOD-BASED PROGRAM
NO.	PROGRAM	PROGRAM OWNERS	% OF ACCOMPLISHMENTS OF TARGET ACTIVITIES FOR Q1	% OF SCHOOLS PROVIDED TA	GAPS	RECOMMENDATIONS	MANAGEMENT RESPONSE	Q2 Compliance
					(Deduced from factors)	(FD Chief/ ASDS)	(SDS)
1	School Establishment Program	Donabel D. Orcullo					Designation of committee on Schools Establishment (for memo)
2	Human Resource Development Program	Dr. Margie Q. Caseres
3	Learning Action Cells (LAC) Program	Dr. Margie Q. Caseres
4	OK sa DepEd	Dr. Yasamen L. Abid	60.00%	100% (26/26)	Absence of medical officer and scheduling constraints resulted in partial implementation of onsite and teleconsultation services in some schools.	Improve coordination with partner health workers and school health focal persons and set a clearer schedule to ensure regular onsite consultations and telehealth services. Since there is no medical officer, maximize available health personnel and establish proper referral and backup systems to ensure continuous service in all schools.		To be implemented in the next quarter with improved coordination and availability of medical personnel to ensure full completion of activities.
5	School Dental Health Care Program	Dr. Yasamen L. Abid	100.00%	100% (26/26)	N/A
6	School-Based Repair and Maintenance Program	Godfrey G. Jimenea
7	School-Based Feeding Program	Grazelle Ann A. Bulibuli
8	Fitness and Wellness Program	Grazelle Ann A. Bulibuli
9	Early Registration	Jerome P. Absin
10	EBEIS/LIS	Jerome P. Absin
11	Oplan Balik Eskwela	Jerome P. Absin
12	School Information Management Program	Jerome P. Absin
13	Strategic Development Planning Program	Jerome P. Absin
14	Brigada Eskwela	Jessie T. Colegio
15	Division Partnership and Linkages Program	Jessie T. Colegio
16	Enhanced School Sports Program	Jessie T. Colegio
17	Adopt-a-School Program	Jessie T. Colegio
18	PTA Affairs Management Program	Jessie T. Colegio
19	School-based Management Program	Queendelyn C. Badilles
20	Child Protection Program	Jhorwin Q. Jumalon
21	Youth Leadership Dev’t Program	Jhorwin Q. Jumalon
22	Child-Friendly School System	Jhorwin Q. Jumalon
23	Adolescent Reproductive Health Program	John Bethto I. Leong
24	Guidance and Counseling Program	John Bethto I. Leong
25	Mental Health and PsychoSocial Support Program	Queenie B. Absin
26	Basic Education Research Program	Queendelyn C. Badilles
27	Field Technical Assistance Program	Jessie T. Colegio
28	Program Implementation Review	Queendelyn C. Badilles
29	Regulatory and Developmental Services for Private Schools Program	Donabel D. Orcullo
30	Dropout Reduction Program (DORP)	Jerome P. Absin
31	Disaster Risk Reduction and Management (DRRM)	Kristine H. Gallardo
32	National Drug Education Program	Queenie B. Absin
33	WINS	Queenie B. Absin

	Consolidated by:

		FD PIR SECRETARIAT

## CID-Cons-QPIR-1stQuarter
1st QUARTER PROGRAM IMPLEMENTATION REVIEW FOR CY 2026-CONSOLIDATED- REPORT- CID
CID-BASED PROGRAM
NO.	PROGRAM	PROGRAM OWNERS	% OF ACCOMPLISHMENTS OF TARGET ACTIVITIES FOR Q1	% OF SCHOOLS PROVIDED TA	GAPS	RECOMMENDATIONS	MANAGEMENT RESPONSE	Q2 Compliance
					(Deduced from factors)	(CID Chief)	(SDS)
1	Alternative Learning System (ALS)	Boy B. Tachado
2	Indigenous People’s Education (IPEd)	Boy B. Tachado
3	ISP - MAPEH	Dr. Emilia M. Baydal
4	Learning Intervention Program	Dr. Emilia M. Baydal
5	ADM/Education in Emergencies	Dr. Enrique Q. Retes
6	Instructional Supervisory Program (ISP)	Dr. Enrique Q. Retes
7	ADM/Education in Emergencies	Dr. Enrique Q. Retes
8	ISP - English	Dr. Hazel Sigrid D. Pederi
9	Reading Remediation Program - English	Dr. Hazel Sigrid D. Pederi
10	Reading Remediation Program - Filipino	Dr. Mark Joseph Q. Espia
11	ISP - Science	Dr. Jose F. Belono
12	Learning Outcomes Assessment Program	Dr. Jose F. Belono
13	ISP - Mathematics	Dr. Rolando Roa
14	Learning Resource Development and Management Program	Dr. Susan T. Balbuena
15	Learning Resource Center Program	Esther Jean Emperwa
16	ISP - TLE	Dr. Symper M. Basiliote
17	ISP - Araling Panlipunan	Dr. Vivian D. Tam
18	Multigrade	Rizza B. Gabuya
19	ISP - Filipino	Dr. Mark Joseph Q. Espia
20	Continuous Improvement (CI) Program	Queendelyn C. Badilles
21	Special Education (SPEd) Program	Juditha B. Paunillan
22	Senior High School Program	Dr. Symper M. Basiliote
23	ISP- TLE	Dr. Symper M. Basiliote
24	ISP - VAL. ED.	Mrs. Rizza B. Gabuya
25	ISP - SNED/ Kindergartin	Mrs. Juditha B. Paunillan
26	ARAL- Reading	Dr. Hazel Sigrid D. Pederi
27	ARAL Math	Dr. Rolando Roa
28	Dynamic Learning Program	Dr. Mark Joseph Q. Espia
29	Testing Coordinator	Juditha B. Paunillan
30	Senior High School Tracking	Symper M. Basiliote
31	GPAK Coor	Symper M. Basiliote

## OSDS-Cons-QPIR-1stQuarter
1st QUARTER PROGRAM IMPLEMENTATION REVIEW FOR CY 2026-CONSOLIDATED- REPORT- OSDS
OSDS-BASED PROGRAM
NO.	PROGRAM	PROGRAM OWNERS	% OF ACCOMPLISHMENTS OF TARGET ACTIVITIES FOR Q1	% OF SCHOOLS PROVIDED TA	GAPS	RECOMMENDATIONS	MANAGEMENT RESPONSE	Q2 Compliance
					(Deduced from factors)	(FD Chief/ ASDS)	(SDS)
1	Office Housekeeping Program (OSDS)	Maricris D. Maribao
2	Field Coordination Program	Jane Day E. Anoba
3	Grievance Management Program	Dr. Eduardo L. Lagos
4	PRAISE	Dr. Eduardo L. Lagos
5	Gender and Development (GaD)	Dr. Vivian D. Tam
6	Fiscal Management Program	Menchie / Catubay
7	Client Feedback Program	Mary Grace A. Esconde
8	Office Communications Management Program	Maricris D. Maribao
9	Records Management Program	Maricris D. Maribao
10	Division Utilities and Services Maintenance Program	Mary Grace A. Esconde
11	Division Physical Facilities Improvement and Equipment Maintenance Program	Mary Grace A. Esconde
12	Performance Management Program	Dr. Eduardo L. Lagos
13	Personnel Organizations Management Program	Mary Grace A. Esconde
14	Computerization Program	Mel E. Gacho
15	Internet Connectivity Program	Mel E. Gacho
16	Advocacy, Info Education, and Communication Program	Mel E. Gacho
17	Division ICT Systems and Infrastructure Management Program	Mel E. Gacho
18	Employee Welfare and Benefits Program	Rachel L. Chiong
19	PRIME-HRM	Rachel L. Chiong
20	Sectarian Affairs Program	Rachel L. Chiong
21	Crucial Resources Inventory and Acquisition Program	Rheadian A. Patoc
22	Procurement Management Program	Dr. Eduardo L. Lagos
23	School Titling Program	Atty. Fiameto Baring
	Employee Discipline Management Program	Atty. Fiameto Baring

	24

## {SchoolName}-Cluster {ClusterNumber}-Cons-QPIR-1stQuarter
1st QUARTER PROGRAM IMPLEMENTATION REVIEW FOR CY 2026-CONSOLIDATED- REPORT- OSDS
OSDS-BASED PROGRAM
NO.	PROGRAM	PROGRAM OWNERS	% OF ACCOMPLISHMENTS OF TARGET ACTIVITIES FOR Q1	% OF SCHOOLS PROVIDED TA	GAPS	RECOMMENDATIONS	MANAGEMENT RESPONSE	Q2 Compliance
					(Deduced from factors)	(FD Chief/ ASDS)	(SDS)
1	Office Housekeeping Program (OSDS)	Maricris D. Maribao
2	Field Coordination Program	Jane Day E. Anoba
3	Grievance Management Program	Dr. Eduardo L. Lagos
4	PRAISE	Dr. Eduardo L. Lagos
5	Gender and Development (GaD)	Dr. Vivian D. Tam
6	Fiscal Management Program	Menchie / Catubay
7	Client Feedback Program	Mary Grace A. Esconde
8	Office Communications Management Program	Maricris D. Maribao
9	Records Management Program	Maricris D. Maribao
10	Division Utilities and Services Maintenance Program	Mary Grace A. Esconde
11	Division Physical Facilities Improvement and Equipment Maintenance Program	Mary Grace A. Esconde
12	Performance Management Program	Dr. Eduardo L. Lagos
13	Personnel Organizations Management Program	Mary Grace A. Esconde
14	Computerization Program	Mel E. Gacho
15	Internet Connectivity Program	Mel E. Gacho
16	Advocacy, Info Education, and Communication Program	Mel E. Gacho
17	Division ICT Systems and Infrastructure Management Program	Mel E. Gacho
18	Employee Welfare and Benefits Program	Rachel L. Chiong
19	PRIME-HRM	Rachel L. Chiong
20	Sectarian Affairs Program	Rachel L. Chiong
21	Crucial Resources Inventory and Acquisition Program	Rheadian A. Patoc
22	Procurement Management Program	Dr. Eduardo L. Lagos
23	School Titling Program	Atty. Fiameto Baring
	Employee Discipline Management Program	Atty. Fiameto Baring

	24

## 'file:///D:/DIVISION%20PROGRAMS%20.xlsx'#SGOD PROGRAMS
School Establishment Program	Donabel D. Orcullo
Human Resource Development Program	Dr. Margie Q. Caseres
Learning Action Cells (LAC) Program	Dr. Margie Q. Caseres
OK sa DepEd	Dr. Yasamen L. Abid
School Dental Health Care Program	Dr. Yasamen L. Abid
School-Based Repair and Maintenance Program	Godfrey G. Jimenea
School-Based Feeding Program	Grazelle Ann A. Bulibuli
Fitness and Wellness Program	Grazelle Ann A. Bulibuli
Early Registration	Jerome P. Absin
EBEIS/LIS	Jerome P. Absin
Oplan Balik Eskwela	Jerome P. Absin
School Information Management Program	Jerome P. Absin
Strategic Development Planning Program	Jerome P. Absin
Brigada Eskwela	Jessie T. Colegio
Division Partnership and Linkages Program	Jessie T. Colegio
Enhanced School Sports Program	Jessie T. Colegio
Adopt-a-School Program	Jessie T. Colegio
PTA Affairs Management Program	Jessie T. Colegio
School-based Management Program	Queendelyn C. Badilles
Child Protection Program	Jhorwin Q. Jumalon
Youth Leadership Dev’t Program	Jhorwin Q. Jumalon
Child-Friendly School System	Jhorwin Q. Jumalon
Adolescent Reproductive Health Program	John Bethto I. Leong
Guidance and Counseling Program	John Bethto I. Leong
Mental Health and PsychoSocial Support Program	Queenie B. Absin
Basic Education Research Program	Queendelyn C. Badilles
Field Technical Assistance Program
Program Implementation Review	Queendelyn C. Badilles
Regulatory and Developmental Services for Private Schools Program	Donabel D. Orcullo
Dropout Reduction Program (DORP)	Jerome P. Absin
Disaster Risk Reduction and Management (DRRM)	Kristine H. Gallardo
National Drug Education Program	Queenie B. Absin
WINS	Queenie B. Absin

## 'file:///D:/DIVISION%20PROGRAMS%20.xlsx'#CID PROGRAMS
Alternative Learning System (ALS)	Boy B. Tachado
Indigenous People’s Education (IPEd)	Boy B. Tachado
ISP - MAPEH	Dr. Emilia M. Baydal
Learning Intervention Program	Dr. Emilia M. Baydal
ADM/Education in Emergencies	Dr. Enrique Q. Retes
Instructional Supervisory Program (ISP)	Dr. Enrique Q. Retes
ADM/Education in Emergencies	Dr. Enrique Q. Retes
ISP - English	Dr. Hazel Sigrid D. Pederi
Reading Remediation Program - English	Dr. Hazel Sigrid D. Pederi
Reading Remediation Program - Filipino
ISP - Science	Dr. Jose F. Belono
Learning Outcomes Assessment Program	Dr. Jose F. Belono
ISP - Mathematics	Dr. Rolando Roa
Learning Resource Development and Management Program	Dr. Susan T. Balbuena
Learning Resource Center Program	Esther Jean Emperwa
ISP - TLE	Dr. Symper M. Basiliote
ISP - Araling Panlipunan	Dr. Vivian D. Tam
Multigrade	Rizza B. Gabuya
ISP - Filipino
Continuous Improvement (CI) Program	Queendelyn C. Badilles

Special Education (SPEd) Program	Juditha B. Paunillan
Senior High School Program	Dr. Symper M. Basiliote
ISP- TLE	Dr. Symper M. Basiliote
ISP - VAL. ED.	Mrs. Rizza B. Gabuya
ISP - SNED/ Kindergartin	Mrs. Juditha B. Paunillan
ARAL- Reading	Dr. Hazel Sigrid D. Pederi
ARAL Math	Dr. Rolando Roa
Dynamic Learning Program	Dr. Mark Joseph Q. Espia
Testing Coordinator	Juditha B. Paunillan
Senior High School Tracking	Symper M. Basiliote
GPAK Coor	Symper M. Basiliote

## 'file:///D:/DIVISION%20PROGRAMS%20.xlsx'#OSDS PROGRAMS
Office Housekeeping Program (OSDS)	Maricris D. Maribao
Field Coordination Program	Jane Day E. Anoba
Grievance Management Program	Dr. Eduardo L. Lagos
PRAISE	Dr. Eduardo L. Lagos
Gender and Development (GaD)	Dr. Vivian D. Tam
Fiscal Management Program	Menchie / Catubay
Client Feedback Program	Mary Grace A. Esconde
Office Communications Management Program	Maricris D. Maribao
Records Management Program	Maricris D. Maribao
Division Utilities and Services Maintenance Program	Mary Grace A. Esconde
Division Physical Facilities Improvement and Equipment Maintenance Program	Mary Grace A. Esconde
Performance Management Program	Dr. Eduardo L. Lagos
Personnel Organizations Management Program	Mary Grace A. Esconde
Computerization Program	Mel E. Gacho
Internet Connectivity Program	Mel E. Gacho
Advocacy, Info Education, and Communication Program	Mel E. Gacho
Division ICT Systems and Infrastructure Management Program	Mel E. Gacho
Employee Welfare and Benefits Program	Rachel L. Chiong
PRIME-HRM	Rachel L. Chiong
Sectarian Affairs Program	Rachel L. Chiong
Crucial Resources Inventory and Acquisition Program	Rheadian A. Patoc
Procurement Management Program	Dr. Eduardo L. Lagos
School Titling Program	Atty. Fiameto Baring